## Slide 1
Repainting Phase 2 The Seed
TSK Synergy Sdn Bhd
Work preparation summary

## Slide 2
Project Summary
Item (Painting) | Total
Townhouse 3-Storey | 10 block
Apartment 6-Storey | 8 block
Clubhouse | 1 unit
TNB Substation | 4 unit
Guardhouse | 1 unit

## Slide 3
Team Arrangement (Painting Only)
PM 1
SE 1
SE 2
Team 1
4 Worker
SE / SV
= 3 org
- 2 org
Worker
= 40 org
- 40 org
= 46 org
= Required 5 org in house
= Required minimum 40 org Sub
+ QS 1 + Safety Officer 1
QS + SO
= 2 org
- 2 org
PM
= 1 org
- 1 org
Team 5
Team 2
Team A
Team B
Team 4
4 Worker
8 Worker
8 Worker
4 Worker
4 Worker
Townhouse (3 Storey)
Apartment (6 Storey)
Clubhouse + TNB + Guardhouse
Staging
SV 1 (Salman)
Team 3
4 Worker
Carpark

## Slide 4
Team Arrangement (Maintenance)
PM 1
SE 1
SE 2
Team 1
4 Worker
SE
= 2 org
- 2 org
Worker
= 38 org
- 38 org
+ QS 1 + Safety Officer 1
QS + SO
= 2 org
- 2 org
PM
= 1 org
Team 5
Team 2
Team 3
Team C1
Team 4
4 Worker
4 Worker
2 Worker
4 Worker
4 Worker
Townhouse (3 Storey)
Staging
Apartment (6 Storey)
Clubhouse + TNB + Guardhouse
Carpark
Team B1
8 Worker
Team B2
8 Worker
Gutter
Team A1
4 Worker
Glazing Bar

## Slide 5
Team Arrangement (Overall)
PM 1
SE 1
SE 2
SE
= 2 org
- 2 org
Worker
= 38 org
- 38 org
+ QS 1 + Safety Officer 1
QS + SO
= 2 org
- 2 org
PM
= 1 org
Team B1
2 Worker
Gutter
Team TSK 1
4 Worker
Glazing Bar
Naqibah
Amin, Salman
+ 2 New worker
Nazmi
Amir

## Slide 6
Team Arrangement Minimum Requirement
1. Apartment = 8 block = 3 months (3 weeks per block) = 2 team
2. Townhouse = 10 block = 4 months (1.5 weeks per block) = 1 team
3. Other = 4 months (2 month clubhouse, 1 month TNB, 1 month Guardhouse) = 1 team
4. Staging = 1 team
5. Glazing Bar = 1 team
6. Gutter = 1 team
Total Painting: 5 teams
Total: 7 teams

## Slide 7
Resources allocation
1. Rumah - 1 no
2. Bomlift - 2 nos
4. Staging - 800 set
3. Transport (Hilux) - 2 nos
* Store Provided